Wadden Sea Board

WSB 15
4 November 2015
Wilhelmshaven

__________________________________________________________________

Agenda Item:	5.1 Wadden Sea World Heritage

Subject:	Report Task Group Sustainable Tourism Strategy

Document No.	WSB 15/5.1/3

Date:	19 October 2015

Submitted by:	Chairman TG-STS

__________________________________________________________________

Objective

The Task Group Sustainable Tourism Strategy (TG-STS) met on 15 September 2015.

The attached progress report informs about the activities of TG-STS since WSB 13.

Proposal

The meeting is referred to the proposals in the attached progress report.

Report Task Group Sustainable Tourism Strategy (TG-STS)

Chair/secretariat: Mr Oeds Bijlsma / Mr Harald Marencic

Meeting: TG-STS 14: 15.09.2015

- PROWAD Project

The Interreg IV B North Sea Region Programme project “PROWAD” was conducted from October 2011 – June 2015 (total budged 1.6 Mio €). Project partners: CWSS (lead), National Park administrations Schleswig-Holstein and Lower Saxony, Dutch Ministry of Economic Affairs, Regiecollege Waddenzee, Danish Ministry of Environment, Danish National Park (January to June 2015 only), WWF Germany

A short description of the results of PROWAD since the last TG-STS meeting in December 2014 is given in Annex 1.

At the PROWAD Final Conference on 12 May 2015 in Hamburg, representatives of the three Wadden Sea states, Denmark, Germany and the Netherlands as well as stakeholders discussed the results of the PROWAD project and explored the possibility of continuing this collaboration in the future.

The conference suggested concentrating on World Heritage awareness building through face-to-face communication and joint projects, namely bird watching and bird flyway cooperation, establishment of a transnational World Heritage Cooperation Programme, and extension of the World Heritage education programme to include teacher training courses in the region and additional target audiences by providing tailor-made educational material.

http://www.waddensea-worldheritage.org/news/2015-05-15-tourism-and-nature-conservation-strengthen-collaboration-wadden-sea-world-heritage

- New Interreg Project in preparation

Within the new programme period of the Interreg North Sea Region Programme (Interreg V B), an ‘Expression of Interest’ for a new Wadden Sea Project was submitted by end of June 2015.

The new project “Protect and Prosper – The Wadden Sea World Heritage Partner Link (PROWAD LINK) was submitted with the first call under the programme priority 1 “Thinking growth: Supporting growth in North Sea region economies” together with 10 partners: CWSS (lead), German national park administrations of Schleswig-Holstein, Lower Saxony and Hamburg, Dutch Ministry of Economic Affairs, Province of Fryslan, Danish Wadden Sea National Park, Danish Southwest Business Development, Danish Nature Agency, WWF Germany, with a total budget of 2.65 Mio €, duration April 2016 – March 2019.

The main objectives of the project are:

- To develop structural and governance arrangements for a transnational World Heritage partnership centre and network.

- To establish a transnational qualification and education framework for stakeholders and SMEs.

- To implement a new, vibrant brand image for the entire Wadden Sea World Heritage region.

The project application, an Expression of Interest (EoI), is attached as separate PDF document.

A decision on the EoI is expected in mid of November 2015. In case of a positive assessment, the full application (work plan, budget plan, formal letter of intent form each partner) has to be delivered within 6 months.

In case of positive decision, a first meeting of the project partners will be organized in December 2015 to organize the preparation of the full application.

- Sustainable Tourism Strategy and Action Plan

The TG-STS took stock of the implementation of the strategy and action plan (see Annex 2). A number of activities have already been carried out or finalized in the framework of the PROWAD project (e.g. World Heritage Tool Kit for entrepreneurs, Glocal WH Flyer, other communication, marketing and awareness activities or material), whereas other actions are still ongoing or carried out on regional level.

Further activities, in specific transnational ones, such as development of a WH training and qualification concept, visitor management and monitoring, branding and campaigns, can only be carried out if additional funding is being provided, e.g. by a new Interreg project PROWAD LINK.

Proposal

The WSB is proposed to comment as appropriate on the progress report and the results of the PROWAD project.

ANNEX 1

1. PROWAD Results

All publications and results can be found and downloaded at www.prowad.org

Publicity and Communications

- PROWAD Final Conference, 12 May 2015, Hamburg. Representatives of the three Wadden Sea states, Denmark, Germany and the Netherlands as well as stakeholders discussed the results of the PROWAD project and explored the possibility of continuing this collaboration in the future.

(http://www.prowad.org/news/2015-05-15-tourism-and-nature-conservation-strengthen-collaboration-wadden-sea-world-heritage)

- PROWAD was invited by the UNESCO to the World Heritage Forum in Sanqingshan, China, on 22 -22 May 2015 to present the strategy on linking tourism and conservation in a transboundary World Heritage property.

Development of Sustainable Tourism Offers

- Sample 7 day-tour itineraries for experience the Wadden Sea WH locally in the regions have been developed and initially presented during the ITB in Berlin in March 2015. As the concept was very well received by partners and visitors is an updated layout version and online integration into the new WH webpage an ongoing activity exceeding the PROWAD project.

- WH bird watching offers: The consultant Dr. Pagenkopf in association with the National Park Administration Schleswig-Holsteinisches Wattenmeer conducted a study which analyses available bird watching offers and gives practice examples as well as further recommendations in order to help to tap the potential of bird watching tours.

- A guideline for the creation of sustainable and environmentally friendly World Heritage package holidays has been developed as a case study in the National Park Lower Saxony together with marketing organisation Die Nordsee GmbH as part of a bachelor thesis of Ms Rittinghaus. The useful guideline provides information on what a World Heritage holiday package needs to consist of regarding its content, its activities (conveying the OUV) and its organisation (sustainable and environmentally friendly) to be called a “World Heritage package holiday”. An English summary is in preparation.

- World Heritage Teaching Kit. The teaching resource on sustainable tourism in the Wadden Sea World Heritage Destination has been finalized in a German, Dutch and English version. A Danish version is in preparation is currently being finalized. The material comprises comprehensive background information for teachers as well as a set of worksheets for pupils.

http://www.prowad.org/news/2015-09-24-new-teaching-resource-sustainable-tourism-wadden-sea-world-heritage

Promotion and Marketing of the Wadden Sea

- “Glocal” WH Flyer: For the first time jointly developed and locally adapted flyers enhance the local visibility and understanding of the Wadden Sea as a World Heritage in the various regions along the Wadden Sea coast and give a concrete access to the Wadden Sea World Heritage in the specific regions. Flyers are completed and distributed: SH: 9 regional WH flyers / NL: 9 regional WH flyers / DK: 6 regional WH flyers. Hamburg produces (outside the PROWAD project) as well a glocal flyer in the same layout and with the same content. Lower Saxony will cover and transfer the content of the glocal flyers into their already established own brochures. Due to the great success Schleswig-Holstein has already issued a 2nd edition (80,000 copies).

- Stakeholder Toolkit for Communication and Marketing: The toolkit was created to help bring consistency to the Wadden Sea World Heritage communication and to provide stakeholders with an overview of and easy access to marketing materials and guidelines. English, Danish, German and Dutch versions finalized, interactive pdf in preparation. USB Flash Drive Card which contain all material developed by PROWAD will be distributed to PROWAD partner by end of October 2015.

- Re-launch World Heritage website with experience/PROWAD (integration of online guide, sustainable WH offers, and education material/IWSS) delayed due to lack of manpower in the CWSS. 
In October 2015, The Netherlands provided financial support to contract an external agency finalizing the new website.

Extension target audiences (additional project January – June 2015)

The additional work package from January to June 2015 consists of 3 key activities:

- 1. Collect and communicate best practice examples of sustainable tourism which demonstrate the application of the PROWAD results, and use of the World Heritage

brand as place-making catalyst for regional development.

- Video of best practice examples demonstrating the positive impacts of World Heritage and sustainable development in the Wadden Sea: 11 interviews/stories (max 2 min), including a summary video (as teaser) have been finalized.
https://www.youtube.com/channel/UCYRzxEiSHooIO34pDaiObsw/videos

- 2. Face-to-Face communication

- Presentation of PROWAD at ITB Berlin (4 - 8 March 2015) in hall 4.1. with a standard booth with daily WH programmes organized by CWSS and local partners and with a 14 metres photo exhibition. The stage area was used for one presentation (organized by Alina Claußen, LKN-SH and Sjon de Haan, NL) and one press event (organized by Wachholtz Verlag) as well. During the ITB Congress a panel discussion and a presentation together with ETE on transnational cooperation in sustainable tourism also took place.

http://www.waddensea-worldheritage.org/news/2015-03-09-wadden-sea-world-heritage-itb-2015

A proposal for a presentation at the ITB 2016 is given as a separate document.

- Roadshow concept: An overall approach and an event design were conducted and inaugurated in June 2015 with 14 roadshow stops in Lower Saxony as a pilot. The concept was locally very well received and showed the great interest and the demand of easy accessible information about the tools developed by PROWAD.

- 3. Wadden Sea World Heritage brand management

  - WH brand video: The animated video clip on sustainable nature experience in the Wadden Sea World Heritage Destination has been developed by WWF in a German, English, Dutch and Danish version. The video will be made available to all interested stakeholders to be included in the World Heritage communication of both the tourism and nature conservation sector.

  - World Heritage Cooperation Program for Business Partners: a feasibility study was written by inspektour and NL RNT drawing up an overview of existing programs and cooperation initiatives in the entire Wadden Region that are relevant to the Wadden Sea World Heritage site and analysing the benefits of and opportunities for a transnational World Heritage cooperation program with businesses and establishing how this can contribute to protecting the OUV.

  - Brand Messaging: A proposal for an integrated marketing communications package has been developed that incorporates marketing tools for different target groups, public relations, events, and internal communications has been initiated and will continue in the next months in cooperation with the .

  - WH Campaign Concept: A consortium of a Dutch and German company (Merkmakers, Leeuwarden, DieBrueder, Hamburg/Berlin) has prepared a concept for a World Heritage campaign with support of the PROWAD partners. The concept will be communicated to potential partners and further developed and implemented in a participatory approach in 2016 – 2018.

ANNEX 2

Status Action Plan

The TG-STS will organize the further work on the action plan implementing the strategy in the coming period, in specific concerning the priorities, the involvement of stakeholders on local and regional level, and how to organize and coordinate the regional work, e.g. through existing regional networks or World Heritage working groups.

The regional working groups have already discussed the action plan and prepared proposals how the activities can be implemented (including funding possibilities), who is taking the lead regionally and how this is being coordinated trilaterally ensuring a consistent approach in accordance with the agreed strategy.

Overall, it can be concluded, that a significant number of activities of the action plan has already been taken up within the PROWAD project and the regional working groups which are currently being implemented. Priority activities proposed by the regionals working groups cover a.o.

- Visibility of World Heritage needs to be enhanced with a coherent message and approach trilaterally to ensure that all partner work towards the same, one goal protecting the OUV in One Wadden Sea.

- Development of World Heritage marketing and products which communicates the OUV thus creating and added values of stakeholders,

- Extension of training and qualification of multipliers on World Heritage and sustainable tourism,

- Development of an overall framework for cooperation with business partners (e.g. through national park partner programmes) including the use of the WH brand for commercial purposes (based on joint criteria and quality standards),

- Enhancing environmental friendly mobility (communication, cooperation, pilot projects).

In the following table, on overview on the implementation of the action plan is given.

Action Pan (version 03.05.2013)

Status September 2015

(Costs: Low: below 15,000 Euro, Medium: 15,000 - 75,000 Euro, High: above 75,000 Euro)

| No. | Strategies and Actions | Priority | When | Costs | Expected outcome | Implement. | Stakeholders involved | Regional contact persons | Activities Local / Regional Level | Activities Trilateral Level | Status (15.9.15) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Objective 1 Enhance understanding and appreciation of Wadden Sea World Heritage |  |  |  |  |  |  |  |  |  |  |
| 1.0 | 1. Raise awareness and visibility of World Heritage amongst stakeholders of its benefits for conservation and sustainable tourism (create communication strategy and tools) |  |  |  |  |  |  |  |  |  |  |
| 1.1 | Preparation on information packages for various target groups (flyer, presentation, website) on existing and potential economic benefits of nature conservation. | High | 2014 | Medium | Distributed packages | Preparation of a ppt (max 10 slides) and flyer/website to illustrate economic benefits of nature conservation by PROWAD budget | TG-STS | SH: Christiane Gätje Nds: Arndt Meyer-Vosgerau NL: Sjon de Haan DK NP | Distribution of packages to local stakeholders | Develop consistent info package. | To be done |
| 1.2 | Material for internal marketing (‘WH bible’): establish regular information flow to local entrepreneurs and tourist information (print and website) tailored to the needs of the stakeholders and their marketing activities (e.g. best practice and hands-on examples). | High | 2014 | Medium | Internal Communication Concept | Develop. internal marketing concept. PROWAD newsletter for tourism stakeholder (Sept) to be continued. Tailored newsletter on WH website | TG-STS | SH: Christiane Gätje Nds: Arndt Meyer-Vosgerau NL: Sjon de Haan DK NP | Communicate information to stakeholders, integration into exiting channels | Develop concept and continue PROWAD newsletter. | Ongoing / delayed |
| 1.3 | WH tool box for entrepreneurs (WH texts for various communication channels, photos, adverts, stories, WH product catalogue with prices, online catalogue with products) | High | 2014 | Low | Tool box | PROWAD Toolkit in preparation | TG-STS, TMOs | SH: Christiane Gätje, C.Höfinghoff Nds: Arndt Meyer-Vosgerau, M.Klinke NL: Sjon de Haan, NN DK Thomas Holst Christensen, NN | Distribute and communicate toolkit | Develop toolkit with stakeholders. | DONE |
| 1.4 | Establish a “Wadden Sea World Heritage Day” with common date, motto and activities. | High | 2014 | Low | Regular annual WH Day | Preparation of Campaign 2014 ongoing. TG-WH to decide on WH Day. | TG-WH, TG-STS | SH: Christiane Gätje, V. Knoke Nds: Arndt Meyer-Vosgerau, H. Hebb. NL: Sjon de Haan, B.Baerends DK NP, A H Marboe | Integrate regional events in joint campaign. Support implementation. | Develop concept and implementation plan. | Ongoing / delayed |
| 1.5 | Establish further events for locals and visitors to communicate the world heritage and to create awareness for the OUV, .e.g. art and culture in the world heritage region (such as the daily painting idea or the planned Wadden Summer for 2013) | Medium |  |  |  |  |  |  |  |  |  |
| 1.6 | Continue story campaign in 2014 and improve the utilisation of results for marketing and communication. | Medium | 2014 | Medium | Application of stories in communication |  |  |  |  |  |  |
| 1.7 | Extend official WH website as a central hub for WH information of stakeholders | High | 2014 | Medium | Website with Stakeholder information | Re-launch website in preparation by CWSS with stakeholder info (by WH budget) | TG-WH, TMOs, NPs | SH: Christiane Gätje, C.Höfinghoff Nds: Arndt Meyer-Vosgerau, M.Klinke NL: Sjon de Haan, NN DK NP, NN | Integration of local information, WH activities and offers on new website (WH highlights). | Re-launch by CWSS in Jan 2014. Inclusion of further functionalities in 2014 | Ongoing / delayed |
| 1.8 | Offer talks on World Heritage for locals, regional clubs, etc. for consistent communication. | Medium | ongoing | Low | number of talks and number of visitors |  |  |  |  |  |  |
| 1.9 | Establish a regular forum for debates on the current activities in the region for touristic service providers and other multipliers. | Medium | ongoing | Low | number of forums and number of participants |  |  |  |  |  |  |
| 1.10 | Enhance the visibility of the Wadden Sea World Heritage by jointly developing a consistent set of eye-catchers e.g. World Heritage traffic signs not only for the highways but also for the coastal towns. | High | 2016 | Low | number of signs | WH traffic signs in NL developed for coastal towns (according highway sign) to be promoted by CWSS, TG-WH, TG-STS |  |  | Communication of existing material and traffic signs to stakeholders | Integration into tool kit | DONE / ongoing |
| 2.0 | 2. Provide stakeholders with the capacity and tools to manage tourism efficiently, responsibly and sustainably based on the local context and needs (qualification and training, best practice examples, education, information sharing, networking), |  |  |  |  |  |  |  |  |  |  |
| 2.1 | Developing of a joint concept for WH qualification and training for stakeholders to ensure a high quality and consistency of training throughout the entire World Heritage ( tailor-made training curriculum / training contents, specification of education needs, depending on the target group). | High | 2015 | High | Qualification and Training Concept | PROWAD to prepare a workshop in spring 2014 with stakeholders involved in training and qualification with the aim to prepare a project application for EU funding in 2015. | TMOs, NPs, universities | SH: C. Gätje, C.Höfinghoff, A.Wollesen Nds: A. Meyer-Vosgerau, M.Klinke, Uni NL: Uni Leeuwarden, Groningen, DK NP, NN | Invite stakeholder to contribute in the development. | Develop concept. | Workshop in cooperation with Wadden Academy in preparation, in PROWAD – LINK, in coop. with RPW and Interreg V A (NL/Nds) |
| 2.2 | Provide sufficient resources to enable tourism stakeholder to participate in training and educational programmes. | Medium | 2015 | Medium | Number of participants |  |  |  |  |  |  |
| 2.3 | Exchange information on existing training programmes and information events to be published on the World Heritage website. | High | 2014 | Low | Events on Website | Stakeholders to communicate relevant WNE qualificiatio programmes to the CWSS | All | SH: Christiane Gätje, C.Höfinghoffn Nds: Arndt Meyer-Vosgerau, M.Klinke NL: Sjon de Haan, NN DK NP, NN | Supply CWSS with information on training and qualification. | Communicate on website. | Delayed, |
| 2.4 | Development of tailor-made English courses for service providers for an active use of English language incl. communication and rhetoric training. | Medium | 2016 | High | Regular language courses |  |  |  |  |  |  |
| 2.5 | Training courses for education and upgrading of the local labour force to being qualified to meet the (new) job market. | Medium | 2016 | Medium | Number of training courses |  |  |  |  |  |  |
| 2.6 | Integrate nature conservation, sustainability in tourism and World Heritage in professional training of tourism sector (tourism studies at schools and universities, internal training). | Medium | 2016 |  | No of study courses |  |  |  |  |  |  |
| 3.0 | 3. Develop educational resources and to enhance pride and identification in relation to the Wadden Sea World Heritage (info centres, schools, universities, job training). |  |  |  |  |  |  |  |  |  |  |
| 3.1 | IWSS as coordinator of World Heritage education and to bundle existing programmes and activities on regional level. Continuation of existing successful cooperation with info centers, education programmes, annual workshops, and integration of World Heritage. | High | 2013 | Medium | Annual workplan | IWSS financing ends in 2013. Financing 2014/15 pending decision from NL, D and DK (WSB December, TGC Feb) | Network Group Education (NG-E), TG-WH | SH: V.Knoke, G..Meurs Nds: H.Hebbelmann, J P Kiel NL: B. Baerends, J.Spek / J. Krol DK: A.H. Marboe, U.H.Lützen | IWSS cooperates with educational institutes and info centers. | Development of a World Heritage Education Strategy (pending finances) | Ongoing / end of 2015 |
| 3.2 | Develop educational material in cooperation with info centres to provide multipliers and educational sector with adequate material about Wadden Sea World Heritage. | Medium | 2013 | Medium | World Heritage educational products |  |  |  |  |  |  |
| 3.3 | Integration of World Heritage into existing educational programmes on regional and national level (e.g. Junior Ranger, My Wadden Sea) | Medium | 2015 | Low | WH integrated in existing programmes |  |  |  |  |  |  |
| 3.4 | Develop a concept for a cooperation with educational sector (kindergarten, schools, universities) and development of curricula with Wadden Sea themes. | Medium | 2016 | Medium | Concept for integration of WH in curricula. |  |  |  |  |  |  |
| 3.5 | Establish a Wadden Sea World Heritage Identity (pride and identification of stakeholders) and emotional access to World Heritage amongst children and adults, visitors and locals. | High | 2014 | Medium | World Heritage Identity | Development conceptual approach to further enable emotional access and identity (Brand Paper, communication) by IWSS | NG-E and TG-WH | SH: V.Knoke, G..Meurs Nds: H.Hebbelmann, J P Kiel NL: B. Baerends, J.Spek / J. Krol DK: A.H. Marboe, U.H.Lützen | Enable stakeholders to establish emotional access to WH (identity and pride) | Develop conceptual approach. | Delayed |
|  | Objective 2 Involving stakeholders in tourism management and product development |  |  |  |  |  |  |  |  |  |  |
| 4.0 | 4. Prepare a tourism management and planning scheme for the entire World Heritage that is in line with the OUV of the property (visitor management and guidance, monitoring and assessment of tourism impacts on nature values, infrastructure and sustainable transport), |  |  |  |  |  |  |  |  |  |  |
| 4.0 | Tourism and Visitor management |  |  |  |  |  |  |  |  |  |  |
| 4.1 | Involve tourism sector in planning, implementation and communication of regional / local conservation / management projects to minimize/maintain low level of impacts from recreational activities on OUV. | Medium | ongoing | Low | No. of joint activities and projects |  |  |  |  |  |  |
| 4.2 | Setting up a consistent visitor management plan for the entire World Heritage defining visitor monitoring instruments (see 4.3) , visitor guidance and information (see 4.6, 4.7) to avoid/minimize impacts of tourism on OUV. | Medium | 2017 | High | Visitor Management Plan |  |  |  |  |  |  |
| 4.3 | Development of a monitoring and reporting system to assess impact of tourism on nature values and socio-economy (e.g. monitoring visitor numbers at hot-spots, info centres, sensitive areas, employment and income). | High | 2017 | High | Monitoring System | Workshop to develop a project outline to monitor and assess tourism and recreational activities in cooperation with the UNESCO ST programme to apply for EU funding. |  |  |  |  | delayed |
| 4.4 | Harmonization of basic tourism indicator (no. visitors, overnight,) to assess and compare trends in tourism developments in the Wadden Sea regions (taking into account Eurostat developments) | High | 2017 | Medium | Comparable tourism indicator | (see above) |  |  |  | Within QSR 2016, evaluation of existing indicators | Delayed |
| 4.5 | Develop a code of conduct on tourism activities at a World Heritage Site for communication to tourism stakeholders and tourists. | High | 2015 | Low | Code of conduct | Promoting "Sustainable Tourism in the Wadden Sea" to the stakeholders as defined in the strategy. Develop a more concrete code of conduct in 2014. | TG-STS |  |  |  | NL Boating agreement and harbours, DK in prep. |
| 4.6 | Consistent integration of World Heritage in existing Wadden Sea exhibitions and visitor information systems, and their improvement and further development. | High | 2017 | Medium | WH Integrated in info systems | Band strategy developed as basis to enable integration of WH consistently in exhibition and information systems. Supporting stakeholders in implementation by CWSS | TG-WH, TMOs, NPs |  |  |  | Ongoing on regional level |
| 4.7 | Development of new visitor information system in cooperation with stakeholders to ensure a consistent approach for the entire Wadden Sea (use experiences from Germany) | Medium | 2017 | High | Visitor Info System with WH |  |  |  |  |  |  |
| 4.8 | Develop proposal for a WH wide visitor survey concept based on a PROWAD pilot survey in Germany in 2013. | Medium | 2014 | Medium | WH visitor survey |  |  |  |  |  |  |
| 4.9 | Compile data for a bi-annual tourism barometer / quality monitor for tourism service providers. | Medium | 2017 | Medium | WH tourism barometer |  |  |  |  |  |  |
| 4.10 | Create local (long-term) development strategies for existing and new tourism facilities in the coastal zone and adjacent areas in order to contribute to optimize the tourism flows in relation to sensitive Wadden Sea locations | Medium | 2015 | Medium | Strategies available |  |  |  |  |  |  |
| 4.11 | Sustainable Transport |  |  |  |  |  |  |  | Several activities on regional level (LNG ferries, bus) |  |  |
| 4.11 | Establish regional forums to coordinate and promote sustainable transport and improve public traffic infrastructure for tourism with the aim to improve access to the destination and to contribute to a climate friendly Wadden Sea (e.g. sustainable transport & mobility masterplan) | Medium | 2014 | Low | Regional forums/workshops on sustainable traffic infrastructure |  |  |  |  |  |  |
| 4.12 | Engage transport companies (ferries, trains, busses) in planning and management of sustainable transport to and within the World Heritage destination (e.g. Fahrtziel Natur, Urlauberbus) and to enhance guest satisfaction (e.g. as national park partners) | High | 2014 | Low | Number of joint activities | Establish cooperation with transport companies. | TMOs, NPs, locals |  |  |  | ongoing on regional level (exchange info) |
| 4.13 | Provide, offer and promote (well-proceed) travelling to and from destination by train (e.g. Fahrtziel Natur, RIT Tickets) combined with pick up/drop off service by accommodation | High | 2014 | low | increased numbers of offers with possibility to travel by train | see above |  |  |  |  | ongoing on regional level (exchange info) |
| 4.14 | Enhance communication of existing public transport offers to tourism stakeholders and their guest. Share best practice examples from other regions. | High | 2014 | Low | Information Package on existing offers | see above |  |  |  |  | ongoing on regional level (exchange info) |
| 4.15 | Develop and promote cross-border hiking and biking facilities along Wadden Sea coast (e.g. improve sign posts, develop theme routes, transport facilities to and in the area, integrate North Sea cycle route). | Medium | 2015 | Medium | Catalogue of hiking and biking facilities. |  |  |  |  |  |  |
| 4.16 | Develop a concept to improve the maritime infrastructure across the entire World Heritage site. | Medium | 2017 | High | Cross border concept on maritime infrastructure |  |  |  |  |  |  |
| 5.0 | 5. Provide a strong World Heritage brand as starting point for development of quality products, services and facilities (with common standards and quality schemes), |  |  |  |  |  |  |  |  |  |  |
| 5.1 | Prepare a description of the brand “Wadden Sea World Heritage” to ensure an understanding and a consistent use of brand by stakeholders. | High | 2013 | Low | WH Brand Paper | Final Draft prepared by PROWAD | TG-WH, TG-STS |  |  |  | DONE |
| 5.2 | Develop a trilateral brand strategy how World Heritage can be applied by the stakeholders for marketing and communication (consistent use on websites) including a feasibility study for commercial use. | High | 2014 | Medium | WH Brand Strategy | PROWAD to develop a strategy to communicate the brand including guidelines for the commercial use (licensing, merchandising, partnerships) | TG-WH, TG-STS |  | Develop project and TOR |  | Delayed, in new project |
| 5.3 | Update / amend existing guidelines for the usage of the WH logo by the stakeholders | High | 2013 | Low | Revised Logo Guidelines | CWSS to update guidelines in accordance with the experience so far, including licensing. | TG-WH |  |  |  | DONE |
| 5.4 | Development of a consistent approach for a Wadden Sea wide quality standards for the use of the World Heritage brand in tourism in accommodation, catering and regional products, public transportation and tour-operation, information and interpretation - based on equal high standards and taking into account existing quality labels and certification. | High | 2014 | High | Quality Standards for business partners | PROWAD to develop a proposal for consistent quality standards when using the brand. | TG-STS, TG-WH, Prow ad |  |  | Inventory of partner programmes in the Wadden Sea | Partner study done, next steps in new project |
| 5.5 | Enlarge the National Park Partnership initiative (promotion and information, new sectors), integration of World Heritage, and ensure a consistent approach in the entire WH. | High | 2014 | Medium | Number of partners and sectors | Ongoing | NPs |  |  |  | Ongoing on regional level |
| 5.6 | Introduction of Public-Private Partnership schemes in the Wadden Sea on quality labels and certifications with a consistent approach in the entire World Heritage. | High | 2015 | High | Number of partners and sectors | In preparation | TG-STS, TG-WH, Prowad |  |  |  |  |
| 5.7 | Compile a catalogue of sustainable tourism offers and regional products (based on common quality criteria) | Medium | 2015 | Medium | Catalogue sustainable offers |  |  |  |  |  |  |
| 5.8 | Develop nature experience offers related to World Heritage themes and contents to enable visitors' "magic experience" considering balance between accessibility and vulnerability of places. | High | 2015 | Medium | Catalogue nature experience offers | WH website with nature experience offers ongoing (PROWAD) | TG-STS |  |  |  | Ongoing/delayed |
| 5.9 | Develop and promote a programme for climate-friendly accommodations, gastronomy services and leisure activities within the destination. | Medium | 2016 | Medium | Programme on climate friendly tourism |  |  |  |  |  |  |
| 5.10 | Developing of an integrated service for visitors of the entire World Heritage, covering sustainable transport, accommodation, gastronomy products, information and interpretation (for example service packages) | Medium | 2017 | High | Integrated service packages for sustainable tourism service, products and facilities. |  |  |  |  |  |  |
| 6.0 | 6. Develop a sustainable "Wadden Sea World Heritage Destination" in transboundary cooperation as an added value of the World Heritage status |  |  |  |  |  |  |  |  |  |  |
| 6.1 | Investigate the feasibility of a “Wadden Sea World Heritage Tourism Destination” which contributes to World Heritage protection. | High | 2014 | Medium | Feasibility study | Done in strategy |  |  |  |  | Done |
| 6.2 | Develop and implement a concept for a “Wadden Sea World Heritage Tourism Destination” | Medium | 2015 | High | Destination concept |  |  |  |  |  |  |
| 6.3 | Carry out joint market research (international/national) for the destination. | Medium | 2016 | high | Market Research Study |  |  |  |  |  |  |
|  | Objective 3 Consistent communication and promotion of high quality tourism |  |  |  |  |  |  |  |  |  |  |
| 7.0 | 7. Development of a joint marketing approach for the destination |  |  |  |  |  |  |  |  |  |  |
| 7.1 | Develop and implement a joint marketing strategy for products, services and facilities (including market research) | High | 2015 | High | Marketing Strategy | Develop outline for a marketing project for application of EU funding |  |  | Use of WH label for regional marketing |  | Delayed |
| 7.2 | Joint marketing of existing sustainable products and offers which convey the OUV (concrete themes: bird watching, hiking tours, tidal flats) | High | 2014 | Low | Offers on WH Website | PROWAD to define criteria to promote OUV and compile a set of offers which can be promoted jointly. |  |  |  |  | Delayed |
| 7.3 | Develop a World Heritage internet portal with connection to bookable offers in cooperation with other distribution partners (online portals, tour operators, regional booking systems) | Low | 2017 | medium | Internet portal with bookable offers |  |  |  |  |  |  |
| 7.4 | B2B marketing, promote WH offers towards tour operators and travel agencies | Low | 2015 | Low | Travel agencies promote WH |  |  |  |  |  |  |
| 7.5 | Cooperate with national tourist organization (e.g. in Germany DZT) to integrate Wadden Sea WH themes in international marketing. | High | 2014 | Low | Wadden Sea WH promoted internationally | WH as theme in national promotion (NL visitor centre Amsterdam, DZT theme year) | TG-WH, TMOs, NPs |  |  |  | Ongoing, |
|  | 8. Integration of World Heritage marketing in existing regional and national marketing activities |  |  |  |  |  |  |  |  |  |  |
| 8.1 | Integration of appropriate information about World Heritage and relevance for economic development in all existing communication channels of the stakeholders. | High | 2014 – 2015 | Low | WH Integrated in websites | Ongoing. Internal marketing to promote WH communication and integration in existing channels | TMOs, NPs |  |  |  |  |
| 8.2 | Integration of information about conservation issues and World Heritage in communication and marketing in a consistent approach | High | 2014 - 2015 | Low | Integrated in TMO material | Ongoing, see above |  |  |  |  |  |
| 8.3 | Quality monitoring of existing stakeholders' World Heritage communication and presentation and alignment with joint WH brand to ensure a consistent approach for the entire destination. | High | 2014 | Low | Concept quality assurance marketing | PROWAD to monitor and asses use of brand by stakeholders with recommendations for father development. | TG-STS |  |  |  |  |
|  | 9. Continuation of joint communication and information activities to raise profile and visibility of the Wadden Sea World Heritage (locally, nationally and international) |  |  |  |  |  |  |  |  |  |  |
| 9.1 | Develop and implement a WH information campaign in cooperation with stakeholders | High | 2014-2017 | Medium | Annual campaign work plan | Ongoing by PROWAD. Campaign 2014 in preparation |  |  |  | Concept developed by PROWAD | Ongoing / in 2016-18, |
| 9.2 | Develop and implement merchandising concept including business model (based on feasibility study by PROWAD in 2013) | High | 2014 | Medium | WH Merchandising Concept | Ongoing by PROWAD. Merchandising concept ready. Implementation in preparation. |  |  |  | Pilot project conducted | On hold due to lack of finances |
| 9.3 | Develop and implement concept of an Official WH Guide (App, website, brochure) in four languages. | High | 2014 | Medium | Publication WH Guide | Ongoing by PROWAD. Implemented in website. Publishing in preparation in 2014 |  |  |  |  | Delayed |
| 9.4 | Provide multilingual information on WH on websites of stakeholders | High | 2015 | Low | Multilingual WH info on websites | Support by material from WH website. (see also 8.3) | All |  |  |  | Ongoing |
| 9.5 | Enhance cooperation with media on World Heritage regionally, nationally, and internationally | High | 214 | Medium | WH Media Concept | Development of media partnership concept with major media companies in the framework of the campaign 2014. |  |  |  |  | Ongoing |
| 9.6 | Coordinate the use of new media and social media to enhance engagement and information about WH | Medium | 2014 | Medium | Social media concept |  |  |  |  |  |  |
| 9.7 | Promote existing Wadden Sea events with link to the WH site at the common website / a joint event calendar in four languages. | Medium | 2014 | Low | Wadden Sea WH event calendar |  |  |  |  |  |  |
| 9.8 | Development of local WH-flyers in order to strengthen a concrete local visibility and understanding of WH and identification with WH for touristic stakeholders and visitors (in progress 2013 by PROWAD) | Medium | 2014 | Medium | "glocal" flyer distributed in each region in NL and D | Ongoing by PROWAD | TG-STS |  | Provide information on local visibility of WH | Preparation flyer with general WH info. Integration of local info accordingly. |  |
|  | Objective 4 Derive benefits for Word Heritage and stakeholders |  |  |  |  |  |  |  |  |  |  |
| 10.0 | 10. Increase engagement of stakeholders in trilateral and international activities on World Heritage |  |  |  |  |  |  |  |  |  |  |
| 10.1 | Participation and commitment of stakeholders in trilateral activities and programmes. | High | ongoing | Low | Number of committed stakeholders | Ongoing. High participation in PROWAD. |  |  |  |  | Ongoing |
| 10.2 | Engagement in UNESCO World Heritage Marine Programme and Tourism Programme (e.g. international workshop on European WH sites, Tönning, 15 - 17 April 2013). | High | ongoing | Low | Joint project and activities | Ongoing. Cooperation with other WH sites. Communication of international cooperation. |  |  |  |  | Ongoing |
| 10.3 | Integration of trilateral and international activities in stakeholder communication. | High | ongoing | Low | Number of activities | Ongoing. Support stakeholder with appropriate information via newsletter and website |  |  |  |  | Ongoing / delayed |
| 11.0 | 11. Promote WH and sustainable tourism as an instrument to maintain and enhance life quality of local communities and sustainable regional development |  |  |  |  |  |  |  |  |  |  |
| 11.1 | Integrate World Heritage and Wadden Sea Plan in relevant legislation and management plans on all governmental levels. | High | 2013 | Medium | WH integrated | Intergrade WH in local, regional and national policy and management issues. | All |  |  |  | Ongoing |
| 11.2 | Investigate impact of World Heritage status on economy, society and culture in the Wadden Sea. | Medium | 2017 | Medium | Economic, social and cultural impact study. |  |  |  |  |  | In new project PROWAD LINK |
| 12.0 | 12. Providing financial revenues from high quality tourism for stakeholders as well as for the protection of the World Heritage |  |  |  |  |  |  |  |  |  |  |
| 12.1 | Investigate possibilities of donations/funding of nature and educational projects from tourism sector. | Medium | 2014 | Medium |  |  |  |  |  | PROWAD Study (WWF) | Done |
| 12.2 | Investigate possibilities of (co)-funding of projects by tourism sector or visitors (see also Rebanks study). | Medium | 2014 | Low | Feasibility study |  |  |  |  |  | In new project PROWAD LINK |
| 12.3 | Investigate cooperation with companies in the regions as donators and multipliers. | Medium | 2015 | High |  |  |  |  |  | Feasibility Study Partner Programme | ongoing |